## Summary
CONNECTLY PROJECT — SPRINT SUMMARY
26 Sprints · 416 Tasks · 4 Team Members · 4-day sprint cycle
Member | Sprint Range | # of Sprints | Total Tasks
Member 1 | Sprint 1–5 | 5 | 80
Member 2 | Sprint 6–11 | 6 | 96
Member 3 | Sprint 12–18 | 7 | 112
Member 4 | Sprint 19–26 | 8 | 128
TOTAL | 26 Sprints | 26 | 416
SPRINT INDEX
Sprint # | Sprint Title | Assigned To
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Member 1
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Member 1
3 | WORKER INTERVIEWS & DATA COLLECTION | Member 1
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Member 1
5 | COMMUNITY SURVEY & MARKET VALIDATION | Member 1
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Member 2
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Member 2
8 | PROJECT PLANNING & RISK MANAGEMENT | Member 2
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Member 2
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Member 2
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Member 2
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Member 3
13 | USER AUTHENTICATION & ACCESS CONTROL | Member 3
14 | USER PROFILE MANAGEMENT SYSTEM | Member 3
15 | JOB POSTING & LISTING FUNCTIONALITY | Member 3
16 | JOB SEARCH & APPLICATION PROCESSING | Member 3
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Member 3
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Member 3
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Member 4
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Member 4
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Member 4
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Member 4
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Member 4
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Member 4
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Member 4
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Member 4
How to use: Update the Status and Trello Added? columns on each sheet as work progresses (dropdowns provided). See the 'All Sprints (Master)' tab for the full list, or each member's own tab for just their sprints.

## All Sprints (Master)
CONNECTLY — 26-SPRINT PROJECT TASK TRACKER
Complete task list — 26 sprints, 416 tasks, assigned across 4 team members
Sprint # | Sprint Title | Day | Task # | Subtask Description | Member Name | Status | Trello Added?
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 1 | 1.1.1 | Draft 10 research questions for homeowners | Member 1 | Not Started | No
|  | Day 1 | 1.1.2 | Draft 10 research questions for workers | Member 1 | Not Started | No
|  | Day 1 | 1.1.3 | Review questions with team for relevance | Member 1 | Not Started | No
|  | Day 1 | 1.1.4 | Finalize approved research questions document | Member 1 | Not Started | No
|  | Day 2 | 1.1.5 | Create interview script for homeowners | Member 1 | Not Started | No
|  | Day 2 | 1.1.6 | Create interview script for workers | Member 1 | Not Started | No
|  | Day 2 | 1.1.7 | Test interview scripts with 2 people | Member 1 | Not Started | No
|  | Day 2 | 1.1.8 | Refine interview scripts based on feedback | Member 1 | Not Started | No
|  | Day 3 | 1.1.9 | Create consent forms for interviewees | Member 1 | Not Started | No
|  | Day 3 | 1.1.10 | Print consent forms (10 copies) | Member 1 | Not Started | No
|  | Day 3 | 1.1.11 | Prepare recording equipment/tools | Member 1 | Not Started | No
|  | Day 3 | 1.1.12 | Create interview schedule template | Member 1 | Not Started | No
|  | Day 4 | 1.1.13 | Finalize all research materials | Member 1 | Not Started | No
|  | Day 4 | 1.1.14 | Share materials with team for review | Member 1 | Not Started | No
|  | Day 4 | 1.1.15 | Get final approval from team | Member 1 | Not Started | No
|  | Day 4 | 1.1.16 | Store all documents in Google Drive | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 1 | 1.2.1 | Identify 10 Belhar homeowners to interview | Member 1 | Not Started | No
|  | Day 1 | 1.2.2 | Schedule interview appointments | Member 1 | Not Started | No
|  | Day 1 | 1.2.3 | Conduct interview #1 | Member 1 | Not Started | No
|  | Day 1 | 1.2.4 | Conduct interview #2 | Member 1 | Not Started | No
|  | Day 2 | 1.2.5 | Conduct interview #3 | Member 1 | Not Started | No
|  | Day 2 | 1.2.6 | Conduct interview #4 | Member 1 | Not Started | No
|  | Day 2 | 1.2.7 | Conduct interview #5 | Member 1 | Not Started | No
|  | Day 2 | 1.2.8 | Conduct interview #6 | Member 1 | Not Started | No
|  | Day 3 | 1.2.9 | Conduct interview #7 | Member 1 | Not Started | No
|  | Day 3 | 1.2.10 | Conduct interview #8 | Member 1 | Not Started | No
|  | Day 3 | 1.2.11 | Conduct interview #9 | Member 1 | Not Started | No
|  | Day 3 | 1.2.12 | Conduct interview #10 | Member 1 | Not Started | No
|  | Day 4 | 1.2.13 | Transcribe all homeowner interview responses | Member 1 | Not Started | No
|  | Day 4 | 1.2.14 | Analyze homeowner feedback for patterns | Member 1 | Not Started | No
|  | Day 4 | 1.2.15 | Create homeowner interview summary report | Member 1 | Not Started | No
|  | Day 4 | 1.2.16 | Present findings to team | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 1 | 1.3.1 | Identify 10 local workers to interview | Member 1 | Not Started | No
|  | Day 1 | 1.3.2 | Schedule interview appointments with workers | Member 1 | Not Started | No
|  | Day 1 | 1.3.3 | Conduct worker interview #1 | Member 1 | Not Started | No
|  | Day 1 | 1.3.4 | Conduct worker interview #2 | Member 1 | Not Started | No
|  | Day 2 | 1.3.5 | Conduct worker interview #3 | Member 1 | Not Started | No
|  | Day 2 | 1.3.6 | Conduct worker interview #4 | Member 1 | Not Started | No
|  | Day 2 | 1.3.7 | Conduct worker interview #5 | Member 1 | Not Started | No
|  | Day 2 | 1.3.8 | Conduct worker interview #6 | Member 1 | Not Started | No
|  | Day 3 | 1.3.9 | Conduct worker interview #7 | Member 1 | Not Started | No
|  | Day 3 | 1.3.10 | Conduct worker interview #8 | Member 1 | Not Started | No
|  | Day 3 | 1.3.11 | Conduct worker interview #9 | Member 1 | Not Started | No
|  | Day 3 | 1.3.12 | Conduct worker interview #10 | Member 1 | Not Started | No
|  | Day 4 | 1.3.13 | Transcribe all worker interview responses | Member 1 | Not Started | No
|  | Day 4 | 1.3.14 | Analyze worker feedback for patterns | Member 1 | Not Started | No
|  | Day 4 | 1.3.15 | Create worker interview summary report | Member 1 | Not Started | No
|  | Day 4 | 1.3.16 | Present findings to team | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 1 | 1.4.1 | Research Facebook Marketplace in Belhar | Member 1 | Not Started | No
|  | Day 1 | 1.4.2 | Document Facebook Marketplace strengths/weaknesses | Member 1 | Not Started | No
|  | Day 1 | 1.4.3 | Research Gumtree usage in Western Cape | Member 1 | Not Started | No
|  | Day 1 | 1.4.4 | Document Gumtree strengths/weaknesses | Member 1 | Not Started | No
|  | Day 2 | 1.4.5 | Research local agency pricing models | Member 1 | Not Started | No
|  | Day 2 | 1.4.6 | Document 3 local agencies and their fees | Member 1 | Not Started | No
|  | Day 2 | 1.4.7 | Research word-of-mouth hiring patterns | Member 1 | Not Started | No
|  | Day 2 | 1.4.8 | Document word-of-mouth pros and cons | Member 1 | Not Started | No
|  | Day 3 | 1.4.9 | Research other community job platforms | Member 1 | Not Started | No
|  | Day 3 | 1.4.10 | Document platform features comparison | Member 1 | Not Started | No
|  | Day 3 | 1.4.11 | Create competitor comparison matrix | Member 1 | Not Started | No
|  | Day 3 | 1.4.12 | Identify gaps in competitor offerings | Member 1 | Not Started | No
|  | Day 4 | 1.4.13 | Document our competitive advantages | Member 1 | Not Started | No
|  | Day 4 | 1.4.14 | Create SWOT analysis for Connectly | Member 1 | Not Started | No
|  | Day 4 | 1.4.15 | Create competitive analysis report | Member 1 | Not Started | No
|  | Day 4 | 1.4.16 | Present competitive analysis to team | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 1 | 1.5.1 | Create Google Forms survey for community | Member 1 | Not Started | No
|  | Day 1 | 1.5.2 | Test survey on 3 people for clarity | Member 1 | Not Started | No
|  | Day 1 | 1.5.3 | Finalize survey questions | Member 1 | Not Started | No
|  | Day 1 | 1.5.4 | Share survey in 5 WhatsApp groups | Member 1 | Not Started | No
|  | Day 2 | 1.5.5 | Share survey on Facebook community pages | Member 1 | Not Started | No
|  | Day 2 | 1.5.6 | Share survey via word-of-mouth | Member 1 | Not Started | No
|  | Day 2 | 1.5.7 | Share survey at local community events | Member 1 | Not Started | No
|  | Day 2 | 1.5.8 | Follow up with reminders for survey completion | Member 1 | Not Started | No
|  | Day 3 | 1.5.9 | Collect 50+ survey responses | Member 1 | Not Started | No
|  | Day 3 | 1.5.10 | Analyze survey response data | Member 1 | Not Started | No
|  | Day 3 | 1.5.11 | Create survey results summary report | Member 1 | Not Started | No
|  | Day 3 | 1.5.12 | Identify key insights from survey | Member 1 | Not Started | No
|  | Day 4 | 1.5.13 | Present survey findings to team | Member 1 | Not Started | No
|  | Day 4 | 1.5.14 | Create final research report | Member 1 | Not Started | No
|  | Day 4 | 1.5.15 | Compile all research documents | Member 1 | Not Started | No
|  | Day 4 | 1.5.16 | Store all research in Google Drive | Member 1 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 1 | 2.1.1 | Create Trello account | Member 2 | Not Started | No
|  | Day 1 | 2.1.2 | Create "Connectly Project" board | Member 2 | Not Started | No
|  | Day 1 | 2.1.3 | Create "Backlog" list on board | Member 2 | Not Started | No
|  | Day 1 | 2.1.4 | Create "To Do" list on board | Member 2 | Not Started | No
|  | Day 2 | 2.1.5 | Create "In Progress" list on board | Member 2 | Not Started | No
|  | Day 2 | 2.1.6 | Create "Blocked" list on board | Member 2 | Not Started | No
|  | Day 2 | 2.1.7 | Create "Done" list on board | Member 2 | Not Started | No
|  | Day 2 | 2.1.8 | Create "Sprint Goals" list on board | Member 2 | Not Started | No
|  | Day 3 | 2.1.9 | Add all Epic labels with colors | Member 2 | Not Started | No
|  | Day 3 | 2.1.10 | Add all Priority labels with colors | Member 2 | Not Started | No
|  | Day 3 | 2.1.11 | Invite all team members to Trello board | Member 2 | Not Started | No
|  | Day 3 | 2.1.12 | Confirm all members accepted invitation | Member 2 | Not Started | No
|  | Day 4 | 2.2.1 | Create shared Google Drive folder | Member 2 | Not Started | No
|  | Day 4 | 2.2.2 | Create subfolders (Research/Design/Finance/etc.) | Member 2 | Not Started | No
|  | Day 4 | 2.2.3 | Create shared Google Docs template | Member 2 | Not Started | No
|  | Day 4 | 2.2.4 | Create shared Google Sheets for budget tracking | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 1 | 2.3.1 | Brainstorm required team roles | Member 2 | Not Started | No
|  | Day 1 | 2.3.2 | List team strengths and skills | Member 2 | Not Started | No
|  | Day 1 | 2.3.3 | Assign Project Manager role | Member 2 | Not Started | No
|  | Day 1 | 2.3.4 | Assign Marketing Lead role | Member 2 | Not Started | No
|  | Day 2 | 2.3.5 | Assign Development Lead role | Member 2 | Not Started | No
|  | Day 2 | 2.3.6 | Assign Operations Lead role | Member 2 | Not Started | No
|  | Day 2 | 2.3.7 | Assign Finance Lead role | Member 2 | Not Started | No
|  | Day 2 | 2.3.8 | Assign Customer Support Lead role | Member 2 | Not Started | No
|  | Day 3 | 2.3.9 | Document all role responsibilities | Member 2 | Not Started | No
|  | Day 3 | 2.3.10 | Confirm all members accept their roles | Member 2 | Not Started | No
|  | Day 3 | 2.3.11 | Create team contact list | Member 2 | Not Started | No
|  | Day 3 | 2.3.12 | Create team availability schedule | Member 2 | Not Started | No
|  | Day 4 | 2.4.1 | Create team WhatsApp group | Member 2 | Not Started | No
|  | Day 4 | 2.4.2 | Add all members to WhatsApp group | Member 2 | Not Started | No
|  | Day 4 | 2.4.3 | Set daily stand-up time | Member 2 | Not Started | No
|  | Day 4 | 2.4.4 | Set weekly sprint review time | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 1 | 2.4.5 | Create shared Google Calendar for deadlines | Member 2 | Not Started | No
|  | Day 1 | 2.4.6 | Add all project milestones to calendar | Member 2 | Not Started | No
|  | Day 1 | 2.4.7 | Define meeting agenda template | Member 2 | Not Started | No
|  | Day 1 | 2.4.8 | Schedule first team meeting | Member 2 | Not Started | No
|  | Day 2 | 2.4.9 | Document meeting minutes template | Member 2 | Not Started | No
|  | Day 2 | 2.4.10 | Create decision log document | Member 2 | Not Started | No
|  | Day 2 | 2.4.11 | Define MVP scope document | Member 2 | Not Started | No
|  | Day 2 | 2.4.12 | Define success metrics (KPIs) | Member 2 | Not Started | No
|  | Day 3 | 2.5.1 | Create risk register template | Member 2 | Not Started | No
|  | Day 3 | 2.5.2 | Identify top 5 project risks | Member 2 | Not Started | No
|  | Day 3 | 2.5.3 | Create mitigation plan for each risk | Member 2 | Not Started | No
|  | Day 3 | 2.5.4 | Define communication strategy for users | Member 2 | Not Started | No
|  | Day 4 | 2.5.5 | Create project timeline (Gantt chart) | Member 2 | Not Started | No
|  | Day 4 | 2.5.6 | Define budget tracking process | Member 2 | Not Started | No
|  | Day 4 | 2.5.7 | Create bug/issue tracking system | Member 2 | Not Started | No
|  | Day 4 | 2.5.8 | Finalize and approve project plan | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 1 | 3.1.1 | Brainstorm brand keywords (Trust, Local, etc.) | Member 2 | Not Started | No
|  | Day 1 | 3.1.2 | Vote on top 5 brand keywords | Member 2 | Not Started | No
|  | Day 1 | 3.1.3 | Create brand mood board | Member 2 | Not Started | No
|  | Day 1 | 3.1.4 | Research color psychology for trust | Member 2 | Not Started | No
|  | Day 2 | 3.1.5 | Select primary brand color | Member 2 | Not Started | No
|  | Day 2 | 3.1.6 | Select secondary brand colors | Member 2 | Not Started | No
|  | Day 2 | 3.1.7 | Select brand typography (fonts) | Member 2 | Not Started | No
|  | Day 2 | 3.1.8 | Create brand style guide document | Member 2 | Not Started | No
|  | Day 3 | 3.1.9 | Present style guide to team for feedback | Member 2 | Not Started | No
|  | Day 3 | 3.1.10 | Finalize brand style guide | Member 2 | Not Started | No
|  | Day 3 | 3.2.1 | Brainstorm 10 logo concepts | Member 2 | Not Started | No
|  | Day 3 | 3.2.2 | Sketch rough logo drafts | Member 2 | Not Started | No
|  | Day 4 | 3.2.3 | Create digital logo concept #1 | Member 2 | Not Started | No
|  | Day 4 | 3.2.4 | Create digital logo concept #2 | Member 2 | Not Started | No
|  | Day 4 | 3.2.5 | Create digital logo concept #3 | Member 2 | Not Started | No
|  | Day 4 | 3.2.6 | Present concepts to team for feedback | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 1 | 3.2.7 | Refine chosen logo concept | Member 2 | Not Started | No
|  | Day 1 | 3.2.8 | Create final logo files (PNG, SVG, PDF) | Member 2 | Not Started | No
|  | Day 1 | 3.2.9 | Create app icon version of logo | Member 2 | Not Started | No
|  | Day 1 | 3.2.10 | Create favicon version of logo | Member 2 | Not Started | No
|  | Day 2 | 3.3.1 | Open Figma file from provided link | Member 2 | Not Started | No
|  | Day 2 | 3.3.2 | Review existing design for "Connectly" | Member 2 | Not Started | No
|  | Day 2 | 3.3.3 | Create wireframe for "Post a Job" screen | Member 2 | Not Started | No
|  | Day 2 | 3.3.4 | Create wireframe for "Worker Profile" screen | Member 2 | Not Started | No
|  | Day 3 | 3.3.5 | Create wireframe for "Messaging" screen | Member 2 | Not Started | No
|  | Day 3 | 3.3.6 | Create wireframe for "Dashboard" screen | Member 2 | Not Started | No
|  | Day 3 | 3.3.7 | Create wireframe for "Login/Register" screen | Member 2 | Not Started | No
|  | Day 3 | 3.3.8 | Convert wireframes to high-fidelity designs | Member 2 | Not Started | No
|  | Day 4 | 3.3.9 | Apply brand colors and fonts to designs | Member 2 | Not Started | No
|  | Day 4 | 3.3.10 | Create interactive prototype links between screens | Member 2 | Not Started | No
|  | Day 4 | 3.3.11 | Test prototype with 3 users | Member 2 | Not Started | No
|  | Day 4 | 3.3.12 | Refine prototype based on feedback | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 1 | 3.4.1 | Design Facebook cover photo | Member 2 | Not Started | No
|  | Day 1 | 3.4.2 | Design Instagram profile picture | Member 2 | Not Started | No
|  | Day 1 | 3.4.3 | Design social media post template #1 | Member 2 | Not Started | No
|  | Day 1 | 3.4.4 | Design social media post template #2 | Member 2 | Not Started | No
|  | Day 2 | 3.4.5 | Design WhatsApp group banner | Member 2 | Not Started | No
|  | Day 2 | 3.4.6 | Design flyer template (A6 size) | Member 2 | Not Started | No
|  | Day 2 | 3.4.7 | Design poster template (A3 size) | Member 2 | Not Started | No
|  | Day 2 | 3.4.8 | Design "Coming Soon" landing page | Member 2 | Not Started | No
|  | Day 3 | 3.4.9 | Design brochure for community events | Member 2 | Not Started | No
|  | Day 3 | 3.4.10 | Design email newsletter template | Member 2 | Not Started | No
|  | Day 3 | 3.4.11 | Review all collateral with team | Member 2 | Not Started | No
|  | Day 3 | 3.4.12 | Get final approval on all designs | Member 2 | Not Started | No
|  | Day 4 | 3.4.13 | Export all final design files | Member 2 | Not Started | No
|  | Day 4 | 3.4.14 | Save all files in Google Drive | Member 2 | Not Started | No
|  | Day 4 | 3.4.15 | Create design assets folder | Member 2 | Not Started | No
|  | Day 4 | 3.4.16 | Share final designs with team | Member 2 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 1 | 4.1.1 | Choose development platform (React Native/Flutter) | Member 3 | Not Started | No
|  | Day 1 | 4.1.2 | Set up development environment | Member 3 | Not Started | No
|  | Day 1 | 4.1.3 | Create GitHub repository | Member 3 | Not Started | No
|  | Day 1 | 4.1.4 | Invite team developers to repository | Member 3 | Not Started | No
|  | Day 2 | 4.1.5 | Set up Firebase project | Member 3 | Not Started | No
|  | Day 2 | 4.1.6 | Configure Firebase authentication | Member 3 | Not Started | No
|  | Day 2 | 4.1.7 | Set up Firestore database | Member 3 | Not Started | No
|  | Day 2 | 4.1.8 | Define database schema (Users, Jobs, Messages) | Member 3 | Not Started | No
|  | Day 3 | 4.1.9 | Create database collections | Member 3 | Not Started | No
|  | Day 3 | 4.1.10 | Set up security rules for database | Member 3 | Not Started | No
|  | Day 3 | 4.1.11 | Test database connection | Member 3 | Not Started | No
|  | Day 3 | 4.1.12 | Document database structure | Member 3 | Not Started | No
|  | Day 4 | 4.1.13 | Set up development branch | Member 3 | Not Started | No
|  | Day 4 | 4.1.14 | Create development workflow guide | Member 3 | Not Started | No
|  | Day 4 | 4.1.15 | Share technical setup with team | Member 3 | Not Started | No
|  | Day 4 | 4.1.16 | Conduct technical onboarding session | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 1 | 4.2.1 | Build registration screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.2.2 | Build login screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.2.3 | Build password reset screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.2.4 | Implement email registration | Member 3 | Not Started | No
|  | Day 2 | 4.2.5 | Implement email login | Member 3 | Not Started | No
|  | Day 2 | 4.2.6 | Implement password reset functionality | Member 3 | Not Started | No
|  | Day 2 | 4.2.7 | Implement user logout | Member 3 | Not Started | No
|  | Day 2 | 4.2.8 | Test registration flow (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.2.9 | Test login flow (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.2.10 | Fix bugs found in authentication | Member 3 | Not Started | No
|  | Day 3 | 4.2.11 | Test authentication on Android | Member 3 | Not Started | No
|  | Day 3 | 4.2.12 | Test authentication on iOS | Member 3 | Not Started | No
|  | Day 4 | 4.2.13 | Create authentication error messages | Member 3 | Not Started | No
|  | Day 4 | 4.2.14 | Implement social login (Google/Facebook) | Member 3 | Not Started | No
|  | Day 4 | 4.2.15 | Finalize authentication module | Member 3 | Not Started | No
|  | Day 4 | 4.2.16 | Document authentication module | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 1 | 4.3.1 | Build profile creation screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.3.2 | Build profile viewing screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.3.3 | Build profile editing screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.3.4 | Implement "Employer" profile type | Member 3 | Not Started | No
|  | Day 2 | 4.3.5 | Implement "Worker" profile type | Member 3 | Not Started | No
|  | Day 2 | 4.3.6 | Add skills field for workers | Member 3 | Not Started | No
|  | Day 2 | 4.3.7 | Add experience field for workers | Member 3 | Not Started | No
|  | Day 2 | 4.3.8 | Add rating/review system skeleton | Member 3 | Not Started | No
|  | Day 3 | 4.3.9 | Test profile creation (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.3.10 | Test profile editing (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.3.11 | Test profile viewing (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.3.12 | Fix profile bugs | Member 3 | Not Started | No
|  | Day 4 | 4.3.13 | Add profile photo upload | Member 3 | Not Started | No
|  | Day 4 | 4.3.14 | Add location field for users | Member 3 | Not Started | No
|  | Day 4 | 4.3.15 | Finalize user profiles module | Member 3 | Not Started | No
|  | Day 4 | 4.3.16 | Document user profiles module | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 1 | 4.4.1 | Build "Post a Job" screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.4.2 | Add job title input field | Member 3 | Not Started | No
|  | Day 1 | 4.4.3 | Add job description text area | Member 3 | Not Started | No
|  | Day 1 | 4.4.4 | Add job category dropdown | Member 3 | Not Started | No
|  | Day 2 | 4.4.5 | Add budget/payment input | Member 3 | Not Started | No
|  | Day 2 | 4.4.6 | Add location field (Belhar area) | Member 3 | Not Started | No
|  | Day 2 | 4.4.7 | Add date/time needed field | Member 3 | Not Started | No
|  | Day 2 | 4.4.8 | Implement job posting to database | Member 3 | Not Started | No
|  | Day 3 | 4.4.9 | Implement job post validation | Member 3 | Not Started | No
|  | Day 3 | 4.4.10 | Add job post success message | Member 3 | Not Started | No
|  | Day 3 | 4.4.11 | Test job posting flow (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.4.12 | Fix job posting bugs | Member 3 | Not Started | No
|  | Day 4 | 4.4.13 | Add image upload for job posts | Member 3 | Not Started | No
|  | Day 4 | 4.4.14 | Add job post editing | Member 3 | Not Started | No
|  | Day 4 | 4.4.15 | Finalize job posting module | Member 3 | Not Started | No
|  | Day 4 | 4.4.16 | Document job posting module | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 1 | 4.5.1 | Build job listings screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.5.2 | Implement job search functionality | Member 3 | Not Started | No
|  | Day 1 | 4.5.3 | Implement job filtering by category | Member 3 | Not Started | No
|  | Day 1 | 4.5.4 | Implement job sorting by date | Member 3 | Not Started | No
|  | Day 2 | 4.5.5 | Build job detail screen UI | Member 3 | Not Started | No
|  | Day 2 | 4.5.6 | Display job details from database | Member 3 | Not Started | No
|  | Day 2 | 4.5.7 | Implement "Apply" button functionality | Member 3 | Not Started | No
|  | Day 2 | 4.5.8 | Show applicant count on job card | Member 3 | Not Started | No
|  | Day 3 | 4.5.9 | Test job viewing (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.5.10 | Test job filtering (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.5.11 | Test job search (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.5.12 | Fix bugs in job listings | Member 3 | Not Started | No
|  | Day 4 | 4.5.13 | Add "Save Job" functionality | Member 3 | Not Started | No
|  | Day 4 | 4.5.14 | Add job sharing functionality | Member 3 | Not Started | No
|  | Day 4 | 4.5.15 | Finalize job viewing module | Member 3 | Not Started | No
|  | Day 4 | 4.5.16 | Document job viewing module | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 1 | 4.6.1 | Build chat list screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.6.2 | Build chat conversation screen UI | Member 3 | Not Started | No
|  | Day 1 | 4.6.3 | Implement send message functionality | Member 3 | Not Started | No
|  | Day 1 | 4.6.4 | Implement receive message functionality | Member 3 | Not Started | No
|  | Day 2 | 4.6.5 | Implement real-time chat updates | Member 3 | Not Started | No
|  | Day 2 | 4.6.6 | Add typing indicator | Member 3 | Not Started | No
|  | Day 2 | 4.6.7 | Add message timestamp | Member 3 | Not Started | No
|  | Day 2 | 4.6.8 | Add read receipts | Member 3 | Not Started | No
|  | Day 3 | 4.6.9 | Test messaging between users (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.6.10 | Test real-time updates (QA) | Member 3 | Not Started | No
|  | Day 3 | 4.6.11 | Fix bugs in messaging | Member 3 | Not Started | No
|  | Day 3 | 4.6.12 | Add message delete functionality | Member 3 | Not Started | No
|  | Day 4 | 4.6.13 | Add image sharing in chat | Member 3 | Not Started | No
|  | Day 4 | 4.6.14 | Add chat notifications | Member 3 | Not Started | No
|  | Day 4 | 4.6.15 | Finalize messaging module | Member 3 | Not Started | No
|  | Day 4 | 4.6.16 | Document messaging module | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 1 | 4.7.1 | Set up Firebase Cloud Messaging | Member 3 | Not Started | No
|  | Day 1 | 4.7.2 | Implement notification for new job posts | Member 3 | Not Started | No
|  | Day 1 | 4.7.3 | Implement notification for job applications | Member 3 | Not Started | No
|  | Day 1 | 4.7.4 | Implement notification for new messages | Member 3 | Not Started | No
|  | Day 2 | 4.7.5 | Test notification delivery | Member 3 | Not Started | No
|  | Day 2 | 4.7.6 | Fix notification bugs | Member 3 | Not Started | No
|  | Day 2 | 4.7.7 | Add notification settings | Member 3 | Not Started | No
|  | Day 2 | 4.7.8 | Finalize notification system | Member 3 | Not Started | No
|  | Day 3 | 4.8.1 | Perform full app walkthrough testing | Member 3 | Not Started | No
|  | Day 3 | 4.8.2 | Test app on Android device | Member 3 | Not Started | No
|  | Day 3 | 4.8.3 | Test app on iOS device | Member 3 | Not Started | No
|  | Day 3 | 4.8.4 | Test offline mode behavior | Member 3 | Not Started | No
|  | Day 4 | 4.8.5 | Test slow internet scenarios | Member 3 | Not Started | No
|  | Day 4 | 4.8.6 | Perform UAT with 5 users | Member 3 | Not Started | No
|  | Day 4 | 4.8.7 | Create bug report document | Member 3 | Not Started | No
|  | Day 4 | 4.8.8 | Prioritize bugs to fix | Member 3 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 1 | 5.1.1 | Create Facebook Business Page | Member 4 | Not Started | No
|  | Day 1 | 5.1.2 | Add business description to Facebook | Member 4 | Not Started | No
|  | Day 1 | 5.1.3 | Upload logo and cover photo to Facebook | Member 4 | Not Started | No
|  | Day 1 | 5.1.4 | Create Instagram Business Profile | Member 4 | Not Started | No
|  | Day 2 | 5.1.5 | Add business description to Instagram | Member 4 | Not Started | No
|  | Day 2 | 5.1.6 | Upload profile picture to Instagram | Member 4 | Not Started | No
|  | Day 2 | 5.1.7 | Create TikTok Profile | Member 4 | Not Started | No
|  | Day 2 | 5.1.8 | Add bio and profile picture to TikTok | Member 4 | Not Started | No
|  | Day 3 | 5.1.9 | Create WhatsApp Community/Group | Member 4 | Not Started | No
|  | Day 3 | 5.1.10 | Add group description and rules | Member 4 | Not Started | No
|  | Day 3 | 5.1.11 | Connect all social media accounts | Member 4 | Not Started | No
|  | Day 3 | 5.1.12 | Create social media content calendar | Member 4 | Not Started | No
|  | Day 4 | 5.1.13 | Post first welcome message on all platforms | Member 4 | Not Started | No
|  | Day 4 | 5.1.14 | Engage with initial followers | Member 4 | Not Started | No
|  | Day 4 | 5.1.15 | Track social media analytics setup | Member 4 | Not Started | No
|  | Day 4 | 5.1.16 | Share social media plan with team | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 1 | 5.2.1 | Write "Introduction to Connectly" post | Member 4 | Not Started | No
|  | Day 1 | 5.2.2 | Create "How It Works" infographic | Member 4 | Not Started | No
|  | Day 1 | 5.2.3 | Create "Benefits for Employers" video | Member 4 | Not Started | No
|  | Day 1 | 5.2.4 | Create "Benefits for Workers" video | Member 4 | Not Started | No
|  | Day 2 | 5.2.5 | Write 5 community engagement posts | Member 4 | Not Started | No
|  | Day 2 | 5.2.6 | Create "Success Story" template | Member 4 | Not Started | No
|  | Day 2 | 5.2.7 | Create "Tips for Hiring" carousel post | Member 4 | Not Started | No
|  | Day 2 | 5.2.8 | Create "Tips for Workers" carousel post | Member 4 | Not Started | No
|  | Day 3 | 5.2.9 | Design promotional graphics pack (10 images) | Member 4 | Not Started | No
|  | Day 3 | 5.2.10 | Create testimonial graphics template | Member 4 | Not Started | No
|  | Day 3 | 5.2.11 | Write 3 blog posts for website | Member 4 | Not Started | No
|  | Day 3 | 5.2.12 | Create email newsletter content | Member 4 | Not Started | No
|  | Day 4 | 5.2.13 | Review all content with team | Member 4 | Not Started | No
|  | Day 4 | 5.2.14 | Get final content approval | Member 4 | Not Started | No
|  | Day 4 | 5.2.15 | Schedule content for publishing | Member 4 | Not Started | No
|  | Day 4 | 5.2.16 | Organize content in Google Drive | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 1 | 5.3.1 | Write flyer copy content | Member 4 | Not Started | No
|  | Day 1 | 5.3.2 | Review flyer copy with team | Member 4 | Not Started | No
|  | Day 1 | 5.3.3 | Design final flyer in Canva | Member 4 | Not Started | No
|  | Day 1 | 5.3.4 | Get flyer design approved | Member 4 | Not Started | No
|  | Day 2 | 5.3.5 | Print 200 flyers | Member 4 | Not Started | No
|  | Day 2 | 5.3.6 | Cut flyers if needed | Member 4 | Not Started | No
|  | Day 2 | 5.3.7 | Distribute flyers at CPUT campus | Member 4 | Not Started | No
|  | Day 2 | 5.3.8 | Distribute flyers at Belhar taxi rank | Member 4 | Not Started | No
|  | Day 3 | 5.3.9 | Distribute flyers at Belhar shopping centers | Member 4 | Not Started | No
|  | Day 3 | 5.3.10 | Distribute flyers at local churches | Member 4 | Not Started | No
|  | Day 3 | 5.3.11 | Distribute flyers at local schools | Member 4 | Not Started | No
|  | Day 3 | 5.3.12 | Distribute flyers at community events | Member 4 | Not Started | No
|  | Day 4 | 5.4.1 | Join 5 Belhar community WhatsApp groups | Member 4 | Not Started | No
|  | Day 4 | 5.4.2 | Introduce Connectly to WhatsApp groups | Member 4 | Not Started | No
|  | Day 4 | 5.4.3 | Share Google Form in WhatsApp groups | Member 4 | Not Started | No
|  | Day 4 | 5.4.4 | Share social media links in WhatsApp groups | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 1 | 5.4.5 | Post daily updates in WhatsApp groups | Member 4 | Not Started | No
|  | Day 1 | 5.4.6 | Respond to questions in WhatsApp groups | Member 4 | Not Started | No
|  | Day 1 | 5.4.7 | Collect phone numbers from interested users | Member 4 | Not Started | No
|  | Day 1 | 5.5.1 | Set up Facebook Ads Manager | Member 4 | Not Started | No
|  | Day 2 | 5.5.2 | Create Facebook ad targeting Belhar residents | Member 4 | Not Started | No
|  | Day 2 | 5.5.3 | Design Facebook ad creative (3 versions) | Member 4 | Not Started | No
|  | Day 2 | 5.5.4 | Launch Facebook ad campaign (R200 budget) | Member 4 | Not Started | No
|  | Day 2 | 5.5.5 | Monitor Facebook ad performance | Member 4 | Not Started | No
|  | Day 3 | 5.5.6 | Set up Instagram Ads | Member 4 | Not Started | No
|  | Day 3 | 5.5.7 | Launch Instagram Stories ads | Member 4 | Not Started | No
|  | Day 3 | 5.5.8 | Monitor Instagram ad performance | Member 4 | Not Started | No
|  | Day 3 | 5.5.9 | Optimize ads based on performance | Member 4 | Not Started | No
|  | Day 4 | 5.5.10 | Report on ad results | Member 4 | Not Started | No
|  | Day 4 | 5.6.1 | Plan 5 TikTok content ideas | Member 4 | Not Started | No
|  | Day 4 | 5.6.2 | Film TikTok video #1 (Introduction) | Member 4 | Not Started | No
|  | Day 4 | 5.6.3 | Edit and Post TikTok video #1 | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 1 | 6.1.1 | Create Employer Onboarding Guide | Member 4 | Not Started | No
|  | Day 1 | 6.1.2 | Create Worker Onboarding Guide | Member 4 | Not Started | No
|  | Day 1 | 6.1.3 | Create FAQ document for users | Member 4 | Not Started | No
|  | Day 1 | 6.1.4 | Create video tutorial for posting jobs | Member 4 | Not Started | No
|  | Day 2 | 6.1.5 | Create video tutorial for applying to jobs | Member 4 | Not Started | No
|  | Day 2 | 6.1.6 | Create video tutorial for messaging | Member 4 | Not Started | No
|  | Day 2 | 6.1.7 | Create "Safe Hiring Tips" guide | Member 4 | Not Started | No
|  | Day 2 | 6.1.8 | Create "Safe Working Tips" guide | Member 4 | Not Started | No
|  | Day 3 | 6.1.9 | Translate guides into Afrikaans | Member 4 | Not Started | No
|  | Day 3 | 6.1.10 | Translate guides into isiXhosa | Member 4 | Not Started | No
|  | Day 3 | 6.2.1 | Define worker verification process | Member 4 | Not Started | No
|  | Day 3 | 6.2.2 | Create worker application form | Member 4 | Not Started | No
|  | Day 4 | 6.2.3 | Design verification badge system | Member 4 | Not Started | No
|  | Day 4 | 6.2.4 | Implement verification check in app | Member 4 | Not Started | No
|  | Day 4 | 6.2.5 | Create verification review process | Member 4 | Not Started | No
|  | Day 4 | 6.2.6 | Verify first 10 workers manually | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 1 | 6.2.7 | Document verification system | Member 4 | Not Started | No
|  | Day 1 | 6.3.1 | Create complaints submission form | Member 4 | Not Started | No
|  | Day 1 | 6.3.2 | Define dispute resolution process | Member 4 | Not Started | No
|  | Day 1 | 6.3.3 | Create dispute logging system | Member 4 | Not Started | No
|  | Day 2 | 6.3.4 | Assign dispute resolution team member | Member 4 | Not Started | No
|  | Day 2 | 6.3.5 | Create complaint response templates | Member 4 | Not Started | No
|  | Day 2 | 6.3.6 | Document dispute resolution procedures | Member 4 | Not Started | No
|  | Day 2 | 6.4.1 | Set up fake job post detection | Member 4 | Not Started | No
|  | Day 3 | 6.4.2 | Create job post approval process | Member 4 | Not Started | No
|  | Day 3 | 6.4.3 | Monitor platform for inappropriate content | Member 4 | Not Started | No
|  | Day 3 | 6.4.4 | Create content moderation guidelines | Member 4 | Not Started | No
|  | Day 3 | 6.4.5 | Set up user reporting system | Member 4 | Not Started | No
|  | Day 4 | 6.4.6 | Create response protocol for reports | Member 4 | Not Started | No
|  | Day 4 | 6.4.7 | Monitor daily active users | Member 4 | Not Started | No
|  | Day 4 | 6.4.8 | Monitor successful job matches | Member 4 | Not Started | No
|  | Day 4 | 6.4.9 | Generate weekly operations report | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 1 | 7.1.1 | Finalize all MVP features | Member 4 | Not Started | No
|  | Day 1 | 7.1.2 | Complete final QA testing | Member 4 | Not Started | No
|  | Day 1 | 7.1.3 | Fix all critical bugs | Member 4 | Not Started | No
|  | Day 1 | 7.1.4 | Prepare app store listings | Member 4 | Not Started | No
|  | Day 2 | 7.1.5 | Write app description for Play Store | Member 4 | Not Started | No
|  | Day 2 | 7.1.6 | Write app description for App Store | Member 4 | Not Started | No
|  | Day 2 | 7.1.7 | Create app screenshots for stores | Member 4 | Not Started | No
|  | Day 2 | 7.1.8 | Create app preview video for stores | Member 4 | Not Started | No
|  | Day 3 | 7.1.9 | Submit app to Google Play Store | Member 4 | Not Started | No
|  | Day 3 | 7.1.10 | Submit app to Apple App Store | Member 4 | Not Started | No
|  | Day 3 | 7.2.1 | Write launch announcement post | Member 4 | Not Started | No
|  | Day 3 | 7.2.2 | Design launch announcement graphic | Member 4 | Not Started | No
|  | Day 4 | 7.2.3 | Record launch video message | Member 4 | Not Started | No
|  | Day 4 | 7.2.4 | Set launch date (target date) | Member 4 | Not Started | No
|  | Day 4 | 7.2.5 | Create launch day schedule/timeline | Member 4 | Not Started | No
|  | Day 4 | 7.2.6 | Assign launch day roles to team | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 1 | 7.2.7 | Send email blast to early sign-ups | Member 4 | Not Started | No
|  | Day 1 | 7.2.8 | Send WhatsApp broadcast to contacts | Member 4 | Not Started | No
|  | Day 1 | 7.2.9 | Coordinate physical launch event | Member 4 | Not Started | No
|  | Day 1 | 7.2.10 | Prepare launch event materials | Member 4 | Not Started | No
|  | Day 2 | 7.3.1 | Post launch announcement on Facebook | Member 4 | Not Started | No
|  | Day 2 | 7.3.2 | Post launch announcement on Instagram | Member 4 | Not Started | No
|  | Day 2 | 7.3.3 | Post launch announcement on TikTok | Member 4 | Not Started | No
|  | Day 2 | 7.3.4 | Post launch announcement in WhatsApp groups | Member 4 | Not Started | No
|  | Day 3 | 7.3.5 | Monitor social media for questions | Member 4 | Not Started | No
|  | Day 3 | 7.3.6 | Respond to launch day inquiries | Member 4 | Not Started | No
|  | Day 3 | 7.3.7 | Track sign-ups on launch day | Member 4 | Not Started | No
|  | Day 3 | 7.3.8 | Track job posts on launch day | Member 4 | Not Started | No
|  | Day 4 | 7.3.9 | Document launch day results | Member 4 | Not Started | No
|  | Day 4 | 7.3.10 | Share launch day results with team | Member 4 | Not Started | No
|  | Day 4 | 7.4.1 | Send "Thank You" message to first users | Member 4 | Not Started | No
|  | Day 4 | 7.4.2 | Create "Welcome to Connectly" email | Member 4 | Not Started | No

## Member 1
MEMBER 1 — Sprints 1–5 (80 tasks)
Sprint # | Sprint Title | Day | Task # | Subtask Description | Member Name | Status | Trello Added?
SPRINT 1 | RESEARCH QUESTIONNAIRE DEVELOPMENT
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 1 | 1.1.1 | Draft 10 research questions for homeowners | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 1 | 1.1.2 | Draft 10 research questions for workers | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 1 | 1.1.3 | Review questions with team for relevance | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 1 | 1.1.4 | Finalize approved research questions document | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 2 | 1.1.5 | Create interview script for homeowners | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 2 | 1.1.6 | Create interview script for workers | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 2 | 1.1.7 | Test interview scripts with 2 people | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 2 | 1.1.8 | Refine interview scripts based on feedback | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 3 | 1.1.9 | Create consent forms for interviewees | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 3 | 1.1.10 | Print consent forms (10 copies) | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 3 | 1.1.11 | Prepare recording equipment/tools | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 3 | 1.1.12 | Create interview schedule template | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 4 | 1.1.13 | Finalize all research materials | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 4 | 1.1.14 | Share materials with team for review | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 4 | 1.1.15 | Get final approval from team | Member 1 | Not Started | No
1 | RESEARCH QUESTIONNAIRE DEVELOPMENT | Day 4 | 1.1.16 | Store all documents in Google Drive | Member 1 | Not Started | No
SPRINT 2 | HOMEOWNER INTERVIEWS & DATA COLLECTION
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 1 | 1.2.1 | Identify 10 Belhar homeowners to interview | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 1 | 1.2.2 | Schedule interview appointments | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 1 | 1.2.3 | Conduct interview #1 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 1 | 1.2.4 | Conduct interview #2 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 2 | 1.2.5 | Conduct interview #3 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 2 | 1.2.6 | Conduct interview #4 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 2 | 1.2.7 | Conduct interview #5 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 2 | 1.2.8 | Conduct interview #6 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 3 | 1.2.9 | Conduct interview #7 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 3 | 1.2.10 | Conduct interview #8 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 3 | 1.2.11 | Conduct interview #9 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 3 | 1.2.12 | Conduct interview #10 | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 4 | 1.2.13 | Transcribe all homeowner interview responses | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 4 | 1.2.14 | Analyze homeowner feedback for patterns | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 4 | 1.2.15 | Create homeowner interview summary report | Member 1 | Not Started | No
2 | HOMEOWNER INTERVIEWS & DATA COLLECTION | Day 4 | 1.2.16 | Present findings to team | Member 1 | Not Started | No
SPRINT 3 | WORKER INTERVIEWS & DATA COLLECTION
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 1 | 1.3.1 | Identify 10 local workers to interview | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 1 | 1.3.2 | Schedule interview appointments with workers | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 1 | 1.3.3 | Conduct worker interview #1 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 1 | 1.3.4 | Conduct worker interview #2 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 2 | 1.3.5 | Conduct worker interview #3 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 2 | 1.3.6 | Conduct worker interview #4 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 2 | 1.3.7 | Conduct worker interview #5 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 2 | 1.3.8 | Conduct worker interview #6 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 3 | 1.3.9 | Conduct worker interview #7 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 3 | 1.3.10 | Conduct worker interview #8 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 3 | 1.3.11 | Conduct worker interview #9 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 3 | 1.3.12 | Conduct worker interview #10 | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 4 | 1.3.13 | Transcribe all worker interview responses | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 4 | 1.3.14 | Analyze worker feedback for patterns | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 4 | 1.3.15 | Create worker interview summary report | Member 1 | Not Started | No
3 | WORKER INTERVIEWS & DATA COLLECTION | Day 4 | 1.3.16 | Present findings to team | Member 1 | Not Started | No
SPRINT 4 | COMPETITOR ANALYSIS & MARKET POSITIONING
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 1 | 1.4.1 | Research Facebook Marketplace in Belhar | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 1 | 1.4.2 | Document Facebook Marketplace strengths/weaknesses | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 1 | 1.4.3 | Research Gumtree usage in Western Cape | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 1 | 1.4.4 | Document Gumtree strengths/weaknesses | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 2 | 1.4.5 | Research local agency pricing models | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 2 | 1.4.6 | Document 3 local agencies and their fees | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 2 | 1.4.7 | Research word-of-mouth hiring patterns | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 2 | 1.4.8 | Document word-of-mouth pros and cons | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 3 | 1.4.9 | Research other community job platforms | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 3 | 1.4.10 | Document platform features comparison | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 3 | 1.4.11 | Create competitor comparison matrix | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 3 | 1.4.12 | Identify gaps in competitor offerings | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 4 | 1.4.13 | Document our competitive advantages | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 4 | 1.4.14 | Create SWOT analysis for Connectly | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 4 | 1.4.15 | Create competitive analysis report | Member 1 | Not Started | No
4 | COMPETITOR ANALYSIS & MARKET POSITIONING | Day 4 | 1.4.16 | Present competitive analysis to team | Member 1 | Not Started | No
SPRINT 5 | COMMUNITY SURVEY & MARKET VALIDATION
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 1 | 1.5.1 | Create Google Forms survey for community | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 1 | 1.5.2 | Test survey on 3 people for clarity | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 1 | 1.5.3 | Finalize survey questions | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 1 | 1.5.4 | Share survey in 5 WhatsApp groups | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 2 | 1.5.5 | Share survey on Facebook community pages | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 2 | 1.5.6 | Share survey via word-of-mouth | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 2 | 1.5.7 | Share survey at local community events | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 2 | 1.5.8 | Follow up with reminders for survey completion | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 3 | 1.5.9 | Collect 50+ survey responses | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 3 | 1.5.10 | Analyze survey response data | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 3 | 1.5.11 | Create survey results summary report | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 3 | 1.5.12 | Identify key insights from survey | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 4 | 1.5.13 | Present survey findings to team | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 4 | 1.5.14 | Create final research report | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 4 | 1.5.15 | Compile all research documents | Member 1 | Not Started | No
5 | COMMUNITY SURVEY & MARKET VALIDATION | Day 4 | 1.5.16 | Store all research in Google Drive | Member 1 | Not Started | No

## Member 2
MEMBER 2 — Sprints 6–11 (96 tasks)
Sprint # | Sprint Title | Day | Task # | Subtask Description | Member Name | Status | Trello Added?
SPRINT 6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 1 | 2.1.1 | Create Trello account | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 1 | 2.1.2 | Create "Connectly Project" board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 1 | 2.1.3 | Create "Backlog" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 1 | 2.1.4 | Create "To Do" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 2 | 2.1.5 | Create "In Progress" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 2 | 2.1.6 | Create "Blocked" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 2 | 2.1.7 | Create "Done" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 2 | 2.1.8 | Create "Sprint Goals" list on board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 3 | 2.1.9 | Add all Epic labels with colors | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 3 | 2.1.10 | Add all Priority labels with colors | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 3 | 2.1.11 | Invite all team members to Trello board | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 3 | 2.1.12 | Confirm all members accepted invitation | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 4 | 2.2.1 | Create shared Google Drive folder | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 4 | 2.2.2 | Create subfolders (Research/Design/Finance/etc.) | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 4 | 2.2.3 | Create shared Google Docs template | Member 2 | Not Started | No
6 | PROJECT MANAGEMENT TOOLS & WORKSPACE SETUP | Day 4 | 2.2.4 | Create shared Google Sheets for budget tracking | Member 2 | Not Started | No
SPRINT 7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 1 | 2.3.1 | Brainstorm required team roles | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 1 | 2.3.2 | List team strengths and skills | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 1 | 2.3.3 | Assign Project Manager role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 1 | 2.3.4 | Assign Marketing Lead role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 2 | 2.3.5 | Assign Development Lead role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 2 | 2.3.6 | Assign Operations Lead role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 2 | 2.3.7 | Assign Finance Lead role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 2 | 2.3.8 | Assign Customer Support Lead role | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 3 | 2.3.9 | Document all role responsibilities | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 3 | 2.3.10 | Confirm all members accept their roles | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 3 | 2.3.11 | Create team contact list | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 3 | 2.3.12 | Create team availability schedule | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 4 | 2.4.1 | Create team WhatsApp group | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 4 | 2.4.2 | Add all members to WhatsApp group | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 4 | 2.4.3 | Set daily stand-up time | Member 2 | Not Started | No
7 | TEAM STRUCTURE & COMMUNICATION PROTOCOLS | Day 4 | 2.4.4 | Set weekly sprint review time | Member 2 | Not Started | No
SPRINT 8 | PROJECT PLANNING & RISK MANAGEMENT
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 1 | 2.4.5 | Create shared Google Calendar for deadlines | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 1 | 2.4.6 | Add all project milestones to calendar | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 1 | 2.4.7 | Define meeting agenda template | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 1 | 2.4.8 | Schedule first team meeting | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 2 | 2.4.9 | Document meeting minutes template | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 2 | 2.4.10 | Create decision log document | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 2 | 2.4.11 | Define MVP scope document | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 2 | 2.4.12 | Define success metrics (KPIs) | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 3 | 2.5.1 | Create risk register template | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 3 | 2.5.2 | Identify top 5 project risks | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 3 | 2.5.3 | Create mitigation plan for each risk | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 3 | 2.5.4 | Define communication strategy for users | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 4 | 2.5.5 | Create project timeline (Gantt chart) | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 4 | 2.5.6 | Define budget tracking process | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 4 | 2.5.7 | Create bug/issue tracking system | Member 2 | Not Started | No
8 | PROJECT PLANNING & RISK MANAGEMENT | Day 4 | 2.5.8 | Finalize and approve project plan | Member 2 | Not Started | No
SPRINT 9 | BRAND IDENTITY & VISUAL STYLE GUIDE
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 1 | 3.1.1 | Brainstorm brand keywords (Trust, Local, etc.) | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 1 | 3.1.2 | Vote on top 5 brand keywords | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 1 | 3.1.3 | Create brand mood board | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 1 | 3.1.4 | Research color psychology for trust | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 2 | 3.1.5 | Select primary brand color | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 2 | 3.1.6 | Select secondary brand colors | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 2 | 3.1.7 | Select brand typography (fonts) | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 2 | 3.1.8 | Create brand style guide document | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 3 | 3.1.9 | Present style guide to team for feedback | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 3 | 3.1.10 | Finalize brand style guide | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 3 | 3.2.1 | Brainstorm 10 logo concepts | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 3 | 3.2.2 | Sketch rough logo drafts | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 4 | 3.2.3 | Create digital logo concept #1 | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 4 | 3.2.4 | Create digital logo concept #2 | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 4 | 3.2.5 | Create digital logo concept #3 | Member 2 | Not Started | No
9 | BRAND IDENTITY & VISUAL STYLE GUIDE | Day 4 | 3.2.6 | Present concepts to team for feedback | Member 2 | Not Started | No
SPRINT 10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 1 | 3.2.7 | Refine chosen logo concept | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 1 | 3.2.8 | Create final logo files (PNG, SVG, PDF) | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 1 | 3.2.9 | Create app icon version of logo | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 1 | 3.2.10 | Create favicon version of logo | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 2 | 3.3.1 | Open Figma file from provided link | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 2 | 3.3.2 | Review existing design for "Connectly" | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 2 | 3.3.3 | Create wireframe for "Post a Job" screen | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 2 | 3.3.4 | Create wireframe for "Worker Profile" screen | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 3 | 3.3.5 | Create wireframe for "Messaging" screen | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 3 | 3.3.6 | Create wireframe for "Dashboard" screen | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 3 | 3.3.7 | Create wireframe for "Login/Register" screen | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 3 | 3.3.8 | Convert wireframes to high-fidelity designs | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 4 | 3.3.9 | Apply brand colors and fonts to designs | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 4 | 3.3.10 | Create interactive prototype links between screens | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 4 | 3.3.11 | Test prototype with 3 users | Member 2 | Not Started | No
10 | APPLICATION PROTOTYPE & USER INTERFACE DESIGN | Day 4 | 3.3.12 | Refine prototype based on feedback | Member 2 | Not Started | No
SPRINT 11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 1 | 3.4.1 | Design Facebook cover photo | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 1 | 3.4.2 | Design Instagram profile picture | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 1 | 3.4.3 | Design social media post template #1 | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 1 | 3.4.4 | Design social media post template #2 | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 2 | 3.4.5 | Design WhatsApp group banner | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 2 | 3.4.6 | Design flyer template (A6 size) | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 2 | 3.4.7 | Design poster template (A3 size) | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 2 | 3.4.8 | Design "Coming Soon" landing page | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 3 | 3.4.9 | Design brochure for community events | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 3 | 3.4.10 | Design email newsletter template | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 3 | 3.4.11 | Review all collateral with team | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 3 | 3.4.12 | Get final approval on all designs | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 4 | 3.4.13 | Export all final design files | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 4 | 3.4.14 | Save all files in Google Drive | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 4 | 3.4.15 | Create design assets folder | Member 2 | Not Started | No
11 | MARKETING COLLATERAL & PROMOTIONAL MATERIALS | Day 4 | 3.4.16 | Share final designs with team | Member 2 | Not Started | No

## Member 3
MEMBER 3 — Sprints 12–18 (112 tasks)
Sprint # | Sprint Title | Day | Task # | Subtask Description | Member Name | Status | Trello Added?
SPRINT 12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 1 | 4.1.1 | Choose development platform (React Native/Flutter) | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 1 | 4.1.2 | Set up development environment | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 1 | 4.1.3 | Create GitHub repository | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 1 | 4.1.4 | Invite team developers to repository | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 2 | 4.1.5 | Set up Firebase project | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 2 | 4.1.6 | Configure Firebase authentication | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 2 | 4.1.7 | Set up Firestore database | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 2 | 4.1.8 | Define database schema (Users, Jobs, Messages) | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 3 | 4.1.9 | Create database collections | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 3 | 4.1.10 | Set up security rules for database | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 3 | 4.1.11 | Test database connection | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 3 | 4.1.12 | Document database structure | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 4 | 4.1.13 | Set up development branch | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 4 | 4.1.14 | Create development workflow guide | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 4 | 4.1.15 | Share technical setup with team | Member 3 | Not Started | No
12 | TECHNICAL INFRASTRUCTURE & DEVELOPMENT SETUP | Day 4 | 4.1.16 | Conduct technical onboarding session | Member 3 | Not Started | No
SPRINT 13 | USER AUTHENTICATION & ACCESS CONTROL
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 1 | 4.2.1 | Build registration screen UI | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 1 | 4.2.2 | Build login screen UI | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 1 | 4.2.3 | Build password reset screen UI | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 1 | 4.2.4 | Implement email registration | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 2 | 4.2.5 | Implement email login | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 2 | 4.2.6 | Implement password reset functionality | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 2 | 4.2.7 | Implement user logout | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 2 | 4.2.8 | Test registration flow (QA) | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 3 | 4.2.9 | Test login flow (QA) | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 3 | 4.2.10 | Fix bugs found in authentication | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 3 | 4.2.11 | Test authentication on Android | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 3 | 4.2.12 | Test authentication on iOS | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 4 | 4.2.13 | Create authentication error messages | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 4 | 4.2.14 | Implement social login (Google/Facebook) | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 4 | 4.2.15 | Finalize authentication module | Member 3 | Not Started | No
13 | USER AUTHENTICATION & ACCESS CONTROL | Day 4 | 4.2.16 | Document authentication module | Member 3 | Not Started | No
SPRINT 14 | USER PROFILE MANAGEMENT SYSTEM
14 | USER PROFILE MANAGEMENT SYSTEM | Day 1 | 4.3.1 | Build profile creation screen UI | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 1 | 4.3.2 | Build profile viewing screen UI | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 1 | 4.3.3 | Build profile editing screen UI | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 1 | 4.3.4 | Implement "Employer" profile type | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 2 | 4.3.5 | Implement "Worker" profile type | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 2 | 4.3.6 | Add skills field for workers | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 2 | 4.3.7 | Add experience field for workers | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 2 | 4.3.8 | Add rating/review system skeleton | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 3 | 4.3.9 | Test profile creation (QA) | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 3 | 4.3.10 | Test profile editing (QA) | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 3 | 4.3.11 | Test profile viewing (QA) | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 3 | 4.3.12 | Fix profile bugs | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 4 | 4.3.13 | Add profile photo upload | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 4 | 4.3.14 | Add location field for users | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 4 | 4.3.15 | Finalize user profiles module | Member 3 | Not Started | No
14 | USER PROFILE MANAGEMENT SYSTEM | Day 4 | 4.3.16 | Document user profiles module | Member 3 | Not Started | No
SPRINT 15 | JOB POSTING & LISTING FUNCTIONALITY
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 1 | 4.4.1 | Build "Post a Job" screen UI | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 1 | 4.4.2 | Add job title input field | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 1 | 4.4.3 | Add job description text area | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 1 | 4.4.4 | Add job category dropdown | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 2 | 4.4.5 | Add budget/payment input | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 2 | 4.4.6 | Add location field (Belhar area) | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 2 | 4.4.7 | Add date/time needed field | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 2 | 4.4.8 | Implement job posting to database | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 3 | 4.4.9 | Implement job post validation | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 3 | 4.4.10 | Add job post success message | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 3 | 4.4.11 | Test job posting flow (QA) | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 3 | 4.4.12 | Fix job posting bugs | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 4 | 4.4.13 | Add image upload for job posts | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 4 | 4.4.14 | Add job post editing | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 4 | 4.4.15 | Finalize job posting module | Member 3 | Not Started | No
15 | JOB POSTING & LISTING FUNCTIONALITY | Day 4 | 4.4.16 | Document job posting module | Member 3 | Not Started | No
SPRINT 16 | JOB SEARCH & APPLICATION PROCESSING
16 | JOB SEARCH & APPLICATION PROCESSING | Day 1 | 4.5.1 | Build job listings screen UI | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 1 | 4.5.2 | Implement job search functionality | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 1 | 4.5.3 | Implement job filtering by category | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 1 | 4.5.4 | Implement job sorting by date | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 2 | 4.5.5 | Build job detail screen UI | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 2 | 4.5.6 | Display job details from database | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 2 | 4.5.7 | Implement "Apply" button functionality | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 2 | 4.5.8 | Show applicant count on job card | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 3 | 4.5.9 | Test job viewing (QA) | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 3 | 4.5.10 | Test job filtering (QA) | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 3 | 4.5.11 | Test job search (QA) | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 3 | 4.5.12 | Fix bugs in job listings | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 4 | 4.5.13 | Add "Save Job" functionality | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 4 | 4.5.14 | Add job sharing functionality | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 4 | 4.5.15 | Finalize job viewing module | Member 3 | Not Started | No
16 | JOB SEARCH & APPLICATION PROCESSING | Day 4 | 4.5.16 | Document job viewing module | Member 3 | Not Started | No
SPRINT 17 | IN-APP MESSAGING & COMMUNICATION SYSTEM
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 1 | 4.6.1 | Build chat list screen UI | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 1 | 4.6.2 | Build chat conversation screen UI | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 1 | 4.6.3 | Implement send message functionality | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 1 | 4.6.4 | Implement receive message functionality | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 2 | 4.6.5 | Implement real-time chat updates | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 2 | 4.6.6 | Add typing indicator | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 2 | 4.6.7 | Add message timestamp | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 2 | 4.6.8 | Add read receipts | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 3 | 4.6.9 | Test messaging between users (QA) | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 3 | 4.6.10 | Test real-time updates (QA) | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 3 | 4.6.11 | Fix bugs in messaging | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 3 | 4.6.12 | Add message delete functionality | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 4 | 4.6.13 | Add image sharing in chat | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 4 | 4.6.14 | Add chat notifications | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 4 | 4.6.15 | Finalize messaging module | Member 3 | Not Started | No
17 | IN-APP MESSAGING & COMMUNICATION SYSTEM | Day 4 | 4.6.16 | Document messaging module | Member 3 | Not Started | No
SPRINT 18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 1 | 4.7.1 | Set up Firebase Cloud Messaging | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 1 | 4.7.2 | Implement notification for new job posts | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 1 | 4.7.3 | Implement notification for job applications | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 1 | 4.7.4 | Implement notification for new messages | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 2 | 4.7.5 | Test notification delivery | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 2 | 4.7.6 | Fix notification bugs | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 2 | 4.7.7 | Add notification settings | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 2 | 4.7.8 | Finalize notification system | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 3 | 4.8.1 | Perform full app walkthrough testing | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 3 | 4.8.2 | Test app on Android device | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 3 | 4.8.3 | Test app on iOS device | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 3 | 4.8.4 | Test offline mode behavior | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 4 | 4.8.5 | Test slow internet scenarios | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 4 | 4.8.6 | Perform UAT with 5 users | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 4 | 4.8.7 | Create bug report document | Member 3 | Not Started | No
18 | PUSH NOTIFICATIONS & SYSTEM INTEGRATION TESTING | Day 4 | 4.8.8 | Prioritize bugs to fix | Member 3 | Not Started | No

## Member 4
MEMBER 4 — Sprints 19–26 (128 tasks)
Sprint # | Sprint Title | Day | Task # | Subtask Description | Member Name | Status | Trello Added?
SPRINT 19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 1 | 5.1.1 | Create Facebook Business Page | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 1 | 5.1.2 | Add business description to Facebook | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 1 | 5.1.3 | Upload logo and cover photo to Facebook | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 1 | 5.1.4 | Create Instagram Business Profile | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 2 | 5.1.5 | Add business description to Instagram | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 2 | 5.1.6 | Upload profile picture to Instagram | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 2 | 5.1.7 | Create TikTok Profile | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 2 | 5.1.8 | Add bio and profile picture to TikTok | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 3 | 5.1.9 | Create WhatsApp Community/Group | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 3 | 5.1.10 | Add group description and rules | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 3 | 5.1.11 | Connect all social media accounts | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 3 | 5.1.12 | Create social media content calendar | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 4 | 5.1.13 | Post first welcome message on all platforms | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 4 | 5.1.14 | Engage with initial followers | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 4 | 5.1.15 | Track social media analytics setup | Member 4 | Not Started | No
19 | SOCIAL MEDIA PRESENCE & DIGITAL BRANDING | Day 4 | 5.1.16 | Share social media plan with team | Member 4 | Not Started | No
SPRINT 20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 1 | 5.2.1 | Write "Introduction to Connectly" post | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 1 | 5.2.2 | Create "How It Works" infographic | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 1 | 5.2.3 | Create "Benefits for Employers" video | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 1 | 5.2.4 | Create "Benefits for Workers" video | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 2 | 5.2.5 | Write 5 community engagement posts | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 2 | 5.2.6 | Create "Success Story" template | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 2 | 5.2.7 | Create "Tips for Hiring" carousel post | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 2 | 5.2.8 | Create "Tips for Workers" carousel post | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 3 | 5.2.9 | Design promotional graphics pack (10 images) | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 3 | 5.2.10 | Create testimonial graphics template | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 3 | 5.2.11 | Write 3 blog posts for website | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 3 | 5.2.12 | Create email newsletter content | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 4 | 5.2.13 | Review all content with team | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 4 | 5.2.14 | Get final content approval | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 4 | 5.2.15 | Schedule content for publishing | Member 4 | Not Started | No
20 | CONTENT STRATEGY & ENGAGEMENT MATERIALS | Day 4 | 5.2.16 | Organize content in Google Drive | Member 4 | Not Started | No
SPRINT 21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 1 | 5.3.1 | Write flyer copy content | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 1 | 5.3.2 | Review flyer copy with team | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 1 | 5.3.3 | Design final flyer in Canva | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 1 | 5.3.4 | Get flyer design approved | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 2 | 5.3.5 | Print 200 flyers | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 2 | 5.3.6 | Cut flyers if needed | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 2 | 5.3.7 | Distribute flyers at CPUT campus | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 2 | 5.3.8 | Distribute flyers at Belhar taxi rank | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 3 | 5.3.9 | Distribute flyers at Belhar shopping centers | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 3 | 5.3.10 | Distribute flyers at local churches | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 3 | 5.3.11 | Distribute flyers at local schools | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 3 | 5.3.12 | Distribute flyers at community events | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 4 | 5.4.1 | Join 5 Belhar community WhatsApp groups | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 4 | 5.4.2 | Introduce Connectly to WhatsApp groups | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 4 | 5.4.3 | Share Google Form in WhatsApp groups | Member 4 | Not Started | No
21 | COMMUNITY OUTREACH & PHYSICAL PROMOTION | Day 4 | 5.4.4 | Share social media links in WhatsApp groups | Member 4 | Not Started | No
SPRINT 22 | DIGITAL ADVERTISING & TIKTOK MARKETING
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 1 | 5.4.5 | Post daily updates in WhatsApp groups | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 1 | 5.4.6 | Respond to questions in WhatsApp groups | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 1 | 5.4.7 | Collect phone numbers from interested users | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 1 | 5.5.1 | Set up Facebook Ads Manager | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 2 | 5.5.2 | Create Facebook ad targeting Belhar residents | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 2 | 5.5.3 | Design Facebook ad creative (3 versions) | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 2 | 5.5.4 | Launch Facebook ad campaign (R200 budget) | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 2 | 5.5.5 | Monitor Facebook ad performance | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 3 | 5.5.6 | Set up Instagram Ads | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 3 | 5.5.7 | Launch Instagram Stories ads | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 3 | 5.5.8 | Monitor Instagram ad performance | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 3 | 5.5.9 | Optimize ads based on performance | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 4 | 5.5.10 | Report on ad results | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 4 | 5.6.1 | Plan 5 TikTok content ideas | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 4 | 5.6.2 | Film TikTok video #1 (Introduction) | Member 4 | Not Started | No
22 | DIGITAL ADVERTISING & TIKTOK MARKETING | Day 4 | 5.6.3 | Edit and Post TikTok video #1 | Member 4 | Not Started | No
SPRINT 23 | USER ONBOARDING & VERIFICATION SYSTEMS
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 1 | 6.1.1 | Create Employer Onboarding Guide | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 1 | 6.1.2 | Create Worker Onboarding Guide | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 1 | 6.1.3 | Create FAQ document for users | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 1 | 6.1.4 | Create video tutorial for posting jobs | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 2 | 6.1.5 | Create video tutorial for applying to jobs | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 2 | 6.1.6 | Create video tutorial for messaging | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 2 | 6.1.7 | Create "Safe Hiring Tips" guide | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 2 | 6.1.8 | Create "Safe Working Tips" guide | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 3 | 6.1.9 | Translate guides into Afrikaans | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 3 | 6.1.10 | Translate guides into isiXhosa | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 3 | 6.2.1 | Define worker verification process | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 3 | 6.2.2 | Create worker application form | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 4 | 6.2.3 | Design verification badge system | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 4 | 6.2.4 | Implement verification check in app | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 4 | 6.2.5 | Create verification review process | Member 4 | Not Started | No
23 | USER ONBOARDING & VERIFICATION SYSTEMS | Day 4 | 6.2.6 | Verify first 10 workers manually | Member 4 | Not Started | No
SPRINT 24 | DISPUTE RESOLUTION & PLATFORM MONITORING
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 1 | 6.2.7 | Document verification system | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 1 | 6.3.1 | Create complaints submission form | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 1 | 6.3.2 | Define dispute resolution process | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 1 | 6.3.3 | Create dispute logging system | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 2 | 6.3.4 | Assign dispute resolution team member | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 2 | 6.3.5 | Create complaint response templates | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 2 | 6.3.6 | Document dispute resolution procedures | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 2 | 6.4.1 | Set up fake job post detection | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 3 | 6.4.2 | Create job post approval process | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 3 | 6.4.3 | Monitor platform for inappropriate content | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 3 | 6.4.4 | Create content moderation guidelines | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 3 | 6.4.5 | Set up user reporting system | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 4 | 6.4.6 | Create response protocol for reports | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 4 | 6.4.7 | Monitor daily active users | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 4 | 6.4.8 | Monitor successful job matches | Member 4 | Not Started | No
24 | DISPUTE RESOLUTION & PLATFORM MONITORING | Day 4 | 6.4.9 | Generate weekly operations report | Member 4 | Not Started | No
SPRINT 25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 1 | 7.1.1 | Finalize all MVP features | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 1 | 7.1.2 | Complete final QA testing | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 1 | 7.1.3 | Fix all critical bugs | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 1 | 7.1.4 | Prepare app store listings | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 2 | 7.1.5 | Write app description for Play Store | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 2 | 7.1.6 | Write app description for App Store | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 2 | 7.1.7 | Create app screenshots for stores | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 2 | 7.1.8 | Create app preview video for stores | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 3 | 7.1.9 | Submit app to Google Play Store | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 3 | 7.1.10 | Submit app to Apple App Store | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 3 | 7.2.1 | Write launch announcement post | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 3 | 7.2.2 | Design launch announcement graphic | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 4 | 7.2.3 | Record launch video message | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 4 | 7.2.4 | Set launch date (target date) | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 4 | 7.2.5 | Create launch day schedule/timeline | Member 4 | Not Started | No
25 | PRE-LAUNCH PREPARATION & CAMPAIGN EXECUTION | Day 4 | 7.2.6 | Assign launch day roles to team | Member 4 | Not Started | No
SPRINT 26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 1 | 7.2.7 | Send email blast to early sign-ups | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 1 | 7.2.8 | Send WhatsApp broadcast to contacts | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 1 | 7.2.9 | Coordinate physical launch event | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 1 | 7.2.10 | Prepare launch event materials | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 2 | 7.3.1 | Post launch announcement on Facebook | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 2 | 7.3.2 | Post launch announcement on Instagram | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 2 | 7.3.3 | Post launch announcement on TikTok | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 2 | 7.3.4 | Post launch announcement in WhatsApp groups | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 3 | 7.3.5 | Monitor social media for questions | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 3 | 7.3.6 | Respond to launch day inquiries | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 3 | 7.3.7 | Track sign-ups on launch day | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 3 | 7.3.8 | Track job posts on launch day | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 4 | 7.3.9 | Document launch day results | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 4 | 7.3.10 | Share launch day results with team | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 4 | 7.4.1 | Send "Thank You" message to first users | Member 4 | Not Started | No
26 | PRODUCT LAUNCH & POST-LAUNCH ACTIVITIES | Day 4 | 7.4.2 | Create "Welcome to Connectly" email | Member 4 | Not Started | No